## Pilot Tracker
P&L Agent Pilot Tracker
Scope: 3 name PNLs. Stakeholders: Agent One platform team and Product Controller business.
# | Activity | Open Question | Dependencies | Team | Answer | Owner and Date
1 | Sandbox access | When can we get access to the finance agent sandbox? | Nothing else starts until we have access | Agent One
2 | Account setup | What permissions or accounts do we need to set up on our end before we can start? | Needed before we can use the sandbox | Agent One
3 | Where the tools run | Where do the agent tools run, in Agent One's environment or on our own servers, and how do they reach MOTIF, BOFC, and the P&L Engine? | Tells us how to build and connect the tools | Agent One
4 | How agents work together | How does Agent One coordinate the different agents working together, and how do they share information between them? | Tells us whether we write the workflow or Agent One provides it | Agent One
5 | How we build agent logic | When we add new behaviour to an agent, do we build it as an MCP, a skill, or a plugin? Which approach do you recommend for our case? | Shapes how each agent is built | Agent One
6 | Login model | How does the agent log into our internal systems? Through a service account, user login, or something else? | Needed before the agent can read internal data | Agent One
7 | Agent One contact | Who from your team is our main contact during the pilot, and who do we call when something breaks? | Who we call when things go wrong | Agent One
8 | Which P&Ls to pilot | Which three P&Ls have you picked for the pilot, and how many trading days should we cover? | Defines what we are actually building | PC
9 | Variance allowed | How close does the agent's P&L number need to be to your manual number? Is that measured in dollars or as a percentage? | Tells us what counts as correct | PC
10 | Scenarios to handle | What situations must the agent handle correctly before we go live? Book errors, market moves, large variances, books not yet ready, anything else? | Defines the tests we need to pass | PC
11 | Time running in parallel | How long should the agent run alongside your existing process before we switch over fully? | Sets the pilot timeline | PC
12 | Daily review process | Who will review the agent's output each day during the parallel run, and where will they see it? | How feedback flows from PC back to us | PC
13 | Validation and rollback | Who has the authority to say the agent is working correctly and approve going live? And if the numbers drift, at what point do we pause and go back to manual? | How we know we are done, and how we exit if needed | PC
14 | PC business contact | Who owns this pilot from the business side? | Our main contact on the PC side | PC